## Budget
Budget Template
Category | Item | Manufacturer | Vendor | Status | Qty | Unit Cost | Total Cost | Example Website
Rocket
Supplies
Travel
[7 empty] | 0 | TOTAL PROJECT COST

## Budget_Example
Budget - Example
Category | Item | Manufacturer | Vendor | Status | Qty | Unit Cost | Total Cost | Example
Rocket
| Rocket Kit | LOC Precision | LOC Precision | Ordered | 2 | 123.29 | 246.58 | ezi-65-mini-0175 – LOC Precision / Public Missiles Ltd.
| Avionics Bay | LOC Precision | LOC Precision | Ordered | 2 | 37.7 | 75.4 | Model Rocket Electronics Bays w/Switch Band - LOC Precision – LOC Precision / Public Missiles Ltd.
| Altimeter 1 | Missileworks |  | On hand | 1 | 79.95 | 79.95 | RRC3 (missileworks.com)
| Switch 1 | Missileworks |  | On hand | 1 | 25 | 25 | Power Switches (missileworks.com)
| Altimeter 2 | Featherweight |  |  | 1 | 175 | 175 | Blue Raven - Featherweight Altimeters
| Switch 2 | Featherweight |  |  | 1 | 25 | 25 | Av-Bay Components - Featherweight Altimeters
| GPS | Featherweight |  |  | 2 | 265 | 530 | Featherweight GPS Tracker (upd) (featherweightaltimeters.com)
| Parachute - Drogue | Rocketman |  |  | 1 | 50 | 50 | The Rocketman's Online Rocket Parachute Store (the-rocketman.com)
| Parachute Protector - Drogue | Rocketman |  | Shipped | 1 | 25 | 25 | The Rocketman's Online Rocket Parachute Store (the-rocketman.com)
| Shock Cord - Drogue | Rocketman |  |  | 1 | 25 | 25 | The Rocketman's Online Rocket Parachute Store (the-rocketman.com)
| Parachute - Main | Sky Angle |  |  | 1 | 100 | 100 | b2 Rocketry Web Site
| Parachute Protector - Main | Sky Angle |  |  | 1 | 25 | 25 | b2 Rocketry Web Site
| Shock Cord - Main | Sky Angle |  |  | 1 | 25 | 25 | b2 Rocketry Web Site
| Miscellaneous Electronics | Wiring, Battery |  |  | 1 | 100 | 100
| Miscellaneous Recovery | Swivels, Quicklinks |  |  | 1 | 100 | 100
Supplies
| Build Supplies | Epoxy, Tooling |  |  |  |  | 200
| Protective Equipment | Gloves, Goggles |  |  |  |  | 200
Travel
| Travel | [5 empty] | 2000 | Needs further breakdown
[7 empty] | 4006.93 | TOTAL PROJECT COST
*note you do not budget for motors - we provide them for you

## Schedule
Schedule Template
Week | Date | Required Milestones | Webinars / Meetings | Formation | Simulation / Research | Procurement | Testing | Build / Assembly | Suggested Team Focus
Week 1 | 2025-01-06 | KickOff | [6 empty] | Team Formation & Resource Acquisition
Week 2 | 2025-01-13 | [7 empty] | Team Formation & Resource Acquisition
Week 3 | 2025-01-20 | [7 empty] | Simulations and Component Research
Week 4 | 2025-01-27 | CDR Document Submission | [6 empty] | Simulations and Component Research
Week 5 | 2025-02-03 | CDR Presentations | [6 empty] | Simulations and Component Research
Week 6 | 2025-02-10 | [7 empty] | Simulations and Component Research
Week 7 | 2025-02-17 | [7 empty] | Procurement and Component Testing
Week 8 | 2025-02-24 | Intermediate Presentations | [6 empty] | Procurement and Component Testing
Week 9 | 2025-03-03 | [7 empty] | Procurement and Component Testing
Week 10 | 2025-03-10 | [7 empty] | Procurement and Component Testing
Week 11 | 2025-03-17 | FRR Document Submission | [6 empty] | Final Build and Assembly
Week 12 | 2025-03-24 | FRR Presentations | [6 empty] | Final Build and Assembly
Week 13 | 2025-03-31 | [7 empty] | Final Build and Assembly
Week 14 | 2025-04-07 | Intermediate Presentations | [6 empty] | Final Build and Assembly
Week 15 | 2025-04-14 | [7 empty] | Final Build and Assembly
Week 16 | 2025-04-21 | Launch Weekend | [6 empty] | Competition Flight
Week 17 | 2025-04-28 | [7 empty] | Flight Assessment
Week 18 | 2025-05-05 | [7 empty] | Flight Assessment
Week 19 | 2025-05-12 | PLAR Documentation | [6 empty] | Flight Assessment
Week 20 | 2025-05-19
Week 21 | 2025-05-26
Week 22 | 2025-06-01 | Announcement of Winners
*note some Webinars were completed in the fall, and the recordings should be reviewed
*add the team meetings, and Webinar dates

## Procurement-Resources
Procurement
You can use the following references to help find a vendor and necessary components - Procurement doesn’t typically begin until design is complete.
You will discuss Procurement in your Virtual Presentation
| Category | Company | State | Link
| Manufacturer | LOC Precision | WI | High Power Model Rocketry Supplies ¦ Advanced Model Rocket Kits – LOC Precision / Public Missiles Ltd.
| Manufacturer | Wildman Rocketry | IL | Rocket Motors, Kits, and Supplies from Wildman Rocketry – wildmanrocketry.com
| Manufacturer | Madcow Rocketry | CA | Madcow Rocketry
| Vendor | Chris Rocketry | GA | Chris' Rocket Supplies, LLC (csrocketry.com)
| Vendor | Apogee Components | CO | Model Rockets & How-To Rocketry Information (apogeerockets.com)
| Vendor | Performance Hobbies | VA | Performance Hobbies Homepage
| Vendor | Giant Leap | OR | Giant Leap Rocketry: High Power Rocketry supplier of parts and kits – GiantLeapRocketry
| Vendor | OffWeGo Rocketry | MN | Off We Go Rocketry
| Vendor | Bay Area Rocketry | CA | Home - Bay Area Rocketry
| Electronics | Featherweight | CA | Featherweight Altimeters - Home
| Electronics | Missileworks | CO | Home (missileworks.com)
| Electronics | AltusMetrum | CO | Altus Metrum
| Electronics | Eggtimer | CA | eggtimer rocketry electronic altimeter gps tracker kit
| Recovery | Sky Angle | GA | b2 Rocketry Web Site
| Recovery | Fruity Chutes | CA | Parachute Manufacturers for Drones, UAV, Rockets, Research ¦ Fruity Chutes
| Recovery | Rocketman | MN | The Rocketman's Online Rocket Parachute Store (the-rocketman.com)
| Motors | Motor Data |  | Rocket Motor Data • ThrustCurve
| Motor Hardware | Aeropack |  | Aero Pack – Aeropack
*reference | Motors | Aerotech Motors |  | AeroTech/Quest Division, RCS Rocket Motor Components, Inc (aerotechstore.com)
*reference | Motors | Cesaroni Motors |  | Cesaroni Technology Incorporated
Other Information
| Tripoli Rocketry Association |  |  | Rocketry Vendors and Resources - Tripoli Rocketry Association
| National Association of Rocketry |  |  | National Association of Rocketry - NAR
| RockSim Simulations |  |  | RockSim Download & Registration : Apogee Rockets, Model Rocketry Excitement Starts Here
*Note you do not procure motors - we provide them for you at Launch Weekend
**Note this list is not exhaustive - provides examples to get you started

## Formation & Resources
Team Formation & Resource Acquisition
At the start of FNL Gateway, your team will need to consider and acquire a number of items which will increase success, by increasing your preparedness:
Person Responsible | Task
Advisor / Students | Team Members (4 - 5 is reasonable, can be more or less)
Students | Team Advisor (should be faculty or staff, associated with school)
Advisor / Students | Rocketry Mentor (will be an experienced Rocketry person from your local area, may or may not be associated with school, may or may not belong to a Prefect)
Advisor | Campus meeting space (suggest team meets weekly)
Advisor | Campus build space (to build the rocket, could be a workshop or classroom)
Advisor | Campus storage space (to store rocket parts and build supplies)
Advisor | Campus computer lab access (to help create documents)
Advisor | Campus shop access (to help build rocket)
Advisor | Any necessary training for computer lab space and shop space
Advisor | Procure RockSim (this should be done immediately - simulations should begin immediately, to understand performance objectives by CDR)
Students | Download Rocksim Trial Version (until full licence is obtained by Advisor)
Advisor | Understanding procurement and grants process of your school (this may delay purchases, if not understood and implemented correctly)

## Simulation & Research
Simulations & Component Research
At the start of FNL Gateway, you should begin simulations which help you make component selections and understand flight performance.
You will also begin to research and understand the required COTS components for a dual deploy rocket.
Person Responsible | Tasks
Advisor | Procure RockSim licences for team (use discount code found in Acceptance Letter, see RockSim instructions in Handbook Appendix)
Students | Download RockSim trial version (until licences are obtained)
Begin to learn RockSim by:
Review RockSim Webinar (see Website)
Review RockSim Video in Series (see Website)
See RockSim Information in Handbook Appendix (see Handbook)
Students | Download and save all FNL25 Gateway RockSim files found on Website (the .rkt files)
Students | Run simulations with all rocket kit and motor combinations from Gateway Handbook Appendix
Goal will be to determine which kit and motor combination you wish to use for Competition
You will present your best choice at CDR
You may change your motor and kit up until 1st Intermediate Review
Students | Begin to research additional rocketry components:
|  | Avionics | You will need to select and purchase 2 COTS altimeters | See Avionics Webinar for support
Please present your choices at CDR - we will need to approve them first, prior to procurement
|  | Tracking | You will need to select and purchase 1 COTS (suggest GPS) tracking device | See Avionics Webinar for support
Please present your choice at CDR - we will need to approve it first, prior to procurement
|  | Recovery | You will need to select and purchase 1 drogue parachute and 1 main parachute (your kit may come with parachutes, but you will likely need to replace them) | See Recovery Webinar for support
Please present your choices at CDR - we will need to approve them first, prior to procurement
There may be additional small components that your rocket needs (that may or may not come with the kit)
Your Rocketry Mentor can help determine all the components you will need.

## Procurement & Testing
Procurement & Testing
After the first Review (CDR) you may begin component procurement and testing.
Final Procurements should take place no later than FRR.
Person Responsible | Task
Advisor | Help facilitate procurements of items for the team (will depend on how your grant is setup).
Ensure proper shipping is selected (rush if needed for example).
Ensure components are received on campus and made accessible to students with minimal delay.
Team Lead | Manage and populate a master components list and budget.
Ensure the Advisor knows what to purchase, and from where (up to students to do the research).
Students | Ensure the components you researched and selected are in the master component list and budget.
Students | Begin testing and understanding component functionality once they arrive.
|  | Altimeters | Ensure you understand the proper handling procedures (do not 'fry' the electronics).
You may test the performance of the altimeter using a vacuum chamber for example.
You may also test the performance of the altimeter by flying it on a drone for example.
Ensure you download / install and understand the user interface (how you program the altimeter and change the settings)
|  | Tracking | Apply similar testing to the GPS tracker
Ensure you download / install and understand the user interface (how you program the GPS and change the settings)
|  | Recovery | You may consider 'drop' tests of the parachutes to verify descent rates and deployments
*Parachute ejections tests only recommended if you have a Rocketry Mentor on campus (otherwise you may omit)
Advisor | Assist students with testing - ensure they have the necessary equipment and supplies.
Students | NOTE: Simulations will continue over the Procurement and Testing phase - you will need to add / update the component weights in to your simulation, to update the performance accuracy.
STRONGLY Suggest you wait until after first review to begin procurements.
Suggest you understand 'lead times' - will it take 4 weeks to arrive? Then you should procure earlier in the schedule. How certain are you this is the component you want? Procure later in schedule.

## Build & Assembly
Final Build & Assembly
Between CDR and FRR (after component procurement and testing) you will begin to assemble your components for Final Build.
Do not rush your build - break down the tasks in to smaller steps, ensure you practice the assembly step (if it involves epoxy for example).
Person Responsible | Task
Advisor | Ensure the team has a space for final assembly of the rocket
Students | Begin final assembly of the subcomponents first
|  | Avionics | Assemble your avionics bay hardware (should have came with the kit)
Verify it is assembled correctly first - then begin to integrate your altimeters, power and switches
Your Rocketry Mentor should verify the layout is correct before assembly
You may also wait until FRR to verify your layout is correct before assembly
|  | Tracking | Similar to Avionics, you may install your tracking in the avionics bay (or alternatively, in the nosecone)
|  | Recovery | Ensure you have all the necessary recovery components (and they are sized correctly) which may include:
Eyebolts, quicklinks, swivels, shock cords, parachute proctectors, drogue parachute, main parachute
You will want to assemble the recovery systems and ensure they fit in the rocket airframe
Begin rocket assembly
Hopefully, someone from your team has taken the L2L Rocketry Workshop (this will better prepare you for rocket assembly)
Your Rocketry Mentor will come in handy, if you have not - will advise you on the sequence and best methods for assembly
Suggest you practice the epoxy steps first (on a scrap part etc) - ensure you understand how long the epoxy takes to set (how much time you have to complete the step)
Break down the epoxy steps (do not try to apply a big batch of epoxy to a bunch of components all at once - like in the workshop) - take your time
You may want / need to purchase or fabricate specific tooling or supplies for assembly
Fin jigs - these will better align your fins and ensure they bond in the correct orientation (better method than 'eyeballing with paper')
Colloidal Silica - this can be added to your epoxy mixture, to thicken to a paste (better method, more control than simply runny epoxy)
Epoxy syringes - this will allow you to apply a bead of (thickened) epoxy in a more controlled manner than scooping with a stick
Angle iron (or extruded aluminum) - this will allow you to align the rail button holes more precisely
You may want to do any cutting, or drilling on a machine (if you have access) instead of hand tools
Milling machine - great for drilling perpendicular to airframe
Lathe - great for cutting / trimming airframes
Advisor | Ensure the students have and use the proper PPE for building
Masks or ventilation for epoxy steps
Gloves for exoxy steps
Students | NOTE: Simulations will continue over the Build / Assembly phase - you will need to add / update the component weights in to your simulation, to update the performance accuracy.
Your final simulation (dimensions, weight, CG) should match what is built (you will need to measure and weigh your fully loaded, built rocket).

## Assessment
Flight Assessment
Post Competition Launch, you will do a comparison between what you expected your rocket to do (from simulations) and what it actually did (from altimeter / GPS data).
You will also reflect on the entire project and provide some lessons learned (what would you change if you had to do it again).
Person Responsible | Task
Advisor | Help wrap up, and secure all parts and supplies in storage for the summer for next years team.
Guide students with lessons learned.
Students | Submit final PLAR powerpoint
Show expected performance
Show actual performance
Discuss the discrepancies
Share some lessons learned
Technical lessons learned (what mistakes were made, how would you correct them)
Project management lessons learned (could you have improved the budget or the schedule)
*Write the lessons learned, such that next years team will benefit from your insight (remind your future self what to avoid)